Cost Management

Cost Management is the process of planning, estimating, budgeting, financing, funding, managing, and controlling project costs so that the project is completed within the approved budget.

Simple Example

You are building a house.

- Estimated Cost = NPR 1 Crore

- Approved Budget = NPR 1 Crore

- Actual Spending after 4 months = NPR 45 Lakhs

Cost management ensures:

- You don't overspend.

- Money is available when required.

- Variance is detected early.

- Corrective actions are taken.

Why Cost Management Matters

Without cost management:

- Project runs out of money

- Profit decreases

- Stakeholders lose confidence

- Schedule delays occur

- Scope gets reduced

- Organization suffers financial loss

Example

A software project was estimated at $500,000.

Without monitoring:

- Developers worked overtime.

- Extra features were added.

- Budget became $700,000.

Project lost $200,000.

Steps of Cost Management

According to standard project management practice, cost management consists of four major processes.

1. Plan Cost Management

Define how project costs will be estimated, tracked and controlled.

Questions answered

- Who approves budget?

- How often costs are reviewed?

- Which estimation method will be used?

- What reports are needed?

Example

A company decides:

- Review cost every Friday.

- Any expense above NPR 1 lakh needs approval.

- Use Bottom-up Estimation.

Output

Cost Management Plan

2. Estimate Costs

Estimate the cost of every activity.

Example

| Activity | Estimated Cost |
| --- | --- |
| UI Design | $5,000 |
| Development | $30,000 |
| Testing | $10,000 |
| Deployment | $5,000 |

Total Estimated Cost

= $50,000

3. Determine Budget

Combine all estimated costs into one approved budget.

Example

Estimated Cost = $50,000

Management Reserve = $5,000

Contingency Reserve = $3,000

Approved Budget

= $58,000

This becomes the Budget at Completion (BAC).

4. Control Costs

Monitor actual spending against the budget.

Example

Budget after 2 months

Expected = $20,000

Actual = $27,000

Difference

= Overspending by $7,000

Manager investigates and takes corrective action.

Types of Cost

1. Direct Cost

Can be directly linked to the project.

Examples

- Developer salary

- Software licenses

- Cloud hosting

- Hardware

2. Indirect Cost

Shared across multiple projects.

Examples

- Office rent

- Electricity

- HR salary

- Internet

3. Fixed Cost

Doesn't change regardless of work.

Examples

- Office rent

- Annual software subscription

4. Variable Cost

Changes with workload.

Examples

- Contractor payment

- Cloud usage

- Overtime

5. Recurring Cost

Occurs repeatedly.

Examples

- Monthly AWS bill

- Internet

- Maintenance

6. Non-recurring Cost

Occurs once.

Examples

- Purchase server

- Buy laptop

7. Operating Cost

Cost to operate the solution.

Examples

- Support

- Hosting

- Monitoring

8. Capital Cost

Investment in assets.

Examples

- Building data center

- Purchasing machines

Types of Cost Estimation

1. Analogous Estimation

Uses previous similar projects.

Fast but less accurate.

Example

Previous website cost

$50,000

Estimate current website

≈ $52,000

2. Parametric Estimation

Uses mathematical models.

Example

One API costs

$300

Need 40 APIs

Estimate

40 × 300

= $12,000

3. Bottom-Up Estimation

Estimate each task individually.

Highest accuracy.

Example

UI = $5,000

Backend = $20,000

Testing = $10,000

Deployment = $5,000

Total

= $40,000

4. Three-Point Estimation (PERT)

Formula

Expected Cost

=(Optimistic + 4×Most Likely + Pessimistic) / 6

Example

Optimistic = 80

Most Likely = 100

Pessimistic = 140

Expected

=(80+400+140)/6

=103.33

5. Expert Judgment

Experts provide estimates.

Example

Senior architect estimates

Migration cost = $100,000

6. Vendor Bid Analysis

Use supplier quotations.

Example

Vendor A

$45,000

Vendor B

$48,000

Vendor C

$43,000

Choose the best value.

Earned Value Management (EVM)

What is EVM?

Earned Value Management (EVM) is a technique that integrates scope, schedule, and cost to measure project performance and forecast future outcomes.

Instead of only asking:

- "How much have we spent?"

EVM also asks:

- "How much work should have been completed?"

- "How much work has actually been completed?"

- "Are we getting good value for the money spent?"

It helps answer:

- Are we ahead or behind schedule?

- Are we under or over budget?

- What is the likely final project cost?

Three Fundamental Values

Assume:

Project Budget (BAC) = $100,000

After Month 5:

- Planned completion = 50%

- Actual completion = 40%

- Actual spending = $55,000

Planned Value (PV)

Budgeted cost of work planned by a certain date.

PV = 50% × 100,000 = $50,000

Interpretation: By now, you planned to complete $50,000 worth of work.

Earned Value (EV)

Budgeted value of the work actually completed.

EV = 40% × 100,000 = $40,000

Interpretation: You have completed only $40,000 worth of planned work.

Actual Cost (AC)

Money actually spent.

AC = $55,000

Interpretation: You spent $55,000.

Variances

Cost Variance (CV)

Formula:
CV = EV − AC

Example:

CV = 40,000 − 55,000 = −15,000

Interpretation:

- Positive CV: Under budget

- Zero: On budget

- Negative CV: Over budget by $15,000

Schedule Variance (SV)

Formula:
SV = EV − PV

Example:

SV = 40,000 − 50,000 = −10,000

Interpretation:

- Positive SV: Ahead of schedule

- Zero: On schedule

- Negative SV: Behind schedule by $10,000 worth of work

Performance Indexes

Cost Performance Index (CPI)

Formula:
CPI = EV / AC

Example:

CPI = 40,000 / 55,000 = 0.73

Interpretation:

- CPI > 1: Under budget

- CPI = 1: On budget

- CPI < 1: Over budget

A CPI of 0.73 means you earn only $0.73 of planned value for every $1 spent.

Schedule Performance Index (SPI)

Formula:
SPI = EV / PV

Example:

SPI = 40,000 / 50,000 = 0.80

Interpretation:

- SPI > 1: Ahead of schedule

- SPI = 1: On schedule

- SPI < 1: Behind schedule

An SPI of 0.80 means the project is progressing at 80% of the planned rate.

Budget at Completion (BAC)

Total approved project budget.

Example:

BAC = $100,000

Estimate at Completion (EAC)

Forecast of the total project cost when completed.

Common Formula (assuming current cost performance continues)

EAC = BAC / CPI

Example:

BAC = $100,000

CPI = 0.73

EAC = 100,000 / 0.73 ≈ $136,986

Interpretation: If performance continues, the project is expected to finish at about $136,986, which is over the original budget.

Another common formula when actual costs are known:

EAC = AC + (BAC − EV) / CPI

Using the example:

EAC = 55,000 + (100,000 − 40,000) / 0.73 ≈ $137,192

Estimate to Complete (ETC)

Expected cost needed to finish the remaining work.

Formula:

ETC = EAC − AC

Example:

ETC = 136,986 − 55,000 = $81,986

Interpretation: Approximately $81,986 more is needed to complete the project.

Variance at Completion (VAC)

Expected budget surplus or deficit at project completion.

Formula:

VAC = BAC − EAC

Example:

VAC = 100,000 − 136,986 = −36,986

Interpretation:

- Positive VAC: Expected to finish under budget

- Zero: On budget

- Negative VAC: Expected to exceed the budget by $36,986

To-Complete Performance Index (TCPI)

Shows the cost efficiency required for the remaining work to meet a target budget.

To meet the original BAC:

TCPI = (BAC − EV) / (BAC − AC)

Example:

TCPI = (100,000 − 40,000) / (100,000 − 55,000)
= 60,000 / 45,000
= 1.33

Interpretation: From now on, the project must achieve a CPI of 1.33 (earn $1.33 of value for every $1 spent) to still finish within the original $100,000 budget, which may be difficult if the current CPI is only 0.73.