Scrum Workshop Activity – Pathao Food Ordering System

Workshop Objective

Demonstrate the complete Scrum lifecycle through a practical project simulation.

Project Example:
Pathao Food Ordering System

System Features:

- Browse restaurants

- Search food

- Add to cart

- Place order

- Online payment

- Track delivery

- Order history

INTRODUCTION TO SCRUM

Scrum Components

Scrum Roles

- Product Owner (PO)

- Scrum Master (SM)

- Development Team

Scrum Artifacts

- Product Backlog

- Sprint Backlog

- Increment

Scrum Ceremonies

- Sprint Planning

- Daily Scrum

- Sprint Review

- Sprint Retrospective

FORM SCRUM TEAM

Product Owner

Represents business/customer needs.

Scrum Master

Facilitates Scrum process.

Development Team

- Frontend Developer

- Backend Developer

- QA Engineer

- UI/UX Designer

- Database Engineer

Example Script

Teacher Says

“Today we are building the Pathao Food Ordering System using Scrum.”

PO Script

“Our goal is to help users order food online quickly and track deliveries easily.”

SM Script

“I will ensure Scrum practices are followed properly and blockers are removed.”

Dev Team Script

“We will collaboratively design, develop, test, and deliver features.”

DEFINE PRODUCT VISION

Product Vision Statement

“Build an online food ordering system where users can browse restaurants, place food orders, pay online, and track deliveries.”

PREPARE PRODUCT BACKLOG

The Product Owner prepares user stories.

Product Backlog Example

| Priority | User Story | Business Value |
| --- | --- | --- |
| High | User registration/login | Critical |
| High | Browse restaurants | Critical |
| High | Add food to cart | Critical |
| High | Place order | Critical |
| Medium | Online payment | High |
| Medium | Order tracking | High |
| Low | Ratings and reviews | Medium |
| Low | Promo coupons | Medium |

Example User Story Format

User Story

“As a customer, I want to add food items to cart so that I can order multiple items together.”

Acceptance Criteria (AC)

- User can add multiple items

- Cart updates total price

- Remove item option available

- Quantity can be modified

STORY SIZING (ESTIMATION)

Use Planning Poker or Fibonacci.

Fibonacci Scale

1, 2, 3, 5, 8, 13

Example Sizing

| User Story | Story Points |
| --- | --- |
| Login | 3 |
| Browse restaurants | 5 |
| Add to cart | 5 |
| Place order | 8 |
| Payment | 8 |

Example Scrum Discussion Script

SM

“Everyone reveal your estimation cards.”

Frontend Dev

“I estimated 5 because cart UI has several states.”

QA

“I estimated 8 because multiple test scenarios exist.”

PO

“Let’s discuss complexity and finalize.”

SPRINT PLANNING

Sprint Duration

2 Weeks

Team Capacity Calculation

| Team Member | Available Days |
| --- | --- |
| Frontend Dev | 10 |
| Backend Dev | 10 |
| QA | 8 |
| Designer | 5 |

Total Capacity Example:

- 30 Story Points

Sprint Goal

“Enable users to browse restaurants and place food items into cart.”

Selected Sprint Backlog

| Story | SP |
| --- | --- |
| Login | 3 |
| Browse restaurants | 5 |
| Add to cart | 5 |
| Restaurant details | 3 |

Total = 16 SP

Sprint Planning Script

PO

“These features are highest priority for business.”

Dev Team

“We commit to delivering these stories within the sprint.”

SM

“Great. Sprint Goal is finalized.”

CREATE TASKS

Break stories into tasks.

Example Tasks

Add to Cart Story

Frontend Tasks

- Design cart page

- Add quantity buttons

Backend Tasks

- Create cart APIs

- Store cart data

QA Tasks

- Test quantity update

- Test invalid items

DAILY SCRUM (DAILY STANDUP)

Duration: 15 Minutes

Each member answers:

- What did I complete yesterday?

- What will I do today?

- Any blockers?

Daily Scrum Example

Frontend Dev

“Yesterday I completed cart UI. Today I will integrate APIs. No blockers.”

Backend Dev

“I completed restaurant API. Blocked by database access.”

SM

“I will coordinate database access after standup.”

MID-SPRINT CHANGE SIMULATION

Now demonstrate changing requirements.

Scenario

PO introduces a new requirement:

“Customers should apply promo coupons in cart.”

Scrum Discussion

PO

“This feature became urgent due to marketing campaign.”

Dev Team

“This impacts sprint capacity.”

SM

“Team should evaluate impact before accepting.”

Decision Example

Team agrees:

- Add simple coupon validation

- Move restaurant reviews to next sprint

DEVELOPMENT & TESTING

Demonstrate collaboration.

QA Example Test Cases

| Test Case | Expected Result |
| --- | --- |
| Add valid item | Item added |
| Remove item | Item removed |
| Empty cart checkout | Error shown |

SPRINT REVIEW

Team demonstrates completed increment.

Sprint Increment Demo

Completed:

- Login

- Browse restaurants

- Add to cart

Pending:

- Online payment

Sprint Review Script

Dev Team

“We completed all committed stories except promo coupon advanced validation.”

PO

“The cart experience looks good, but restaurant filtering should improve.”

Stakeholder Feedback

“Need food category filters.”

Product Backlog Update

PO adds:

- Filter by cuisine

- Search by food item

RETROSPECTIVE

Discuss:

- What went well?

- What went wrong?

- What can improve?

Retrospective Example

| Went Well | Improvement Needed |
| --- | --- |
| Good collaboration | Requirements changed late |
| Daily sync helpful | API testing delayed |

Retrospective Script

SM

“What helped the team most?”

QA

“Daily communication reduced defects.”

Backend Dev

“We need earlier API contract discussion.”

SM

“Action item: API review before development next sprint.”

FINAL SCRUM FLOW SUMMARY

Complete Scrum Lifecycle

- Form Scrum Team

- Define Product Vision

- Create Product Backlog

- Prioritize Stories

- Estimate Stories

- Calculate Capacity

- Sprint Planning

- Define Sprint Goal

- Create Sprint Backlog

- Daily Scrum

- Handle Mid-Sprint Changes

- Development & Testing

- Sprint Review

- Increment Demo

- Retrospective

- Start Next Sprint

ARTIFACTS CREATED DURING WORKSHOP

Product Backlog

Master requirement list.

Sprint Backlog

Selected sprint stories/tasks.

Increment

Working software delivered.

IMPORTANT SCRUM LEARNINGS TO EXPLAIN

Scrum is iterative
Scrum welcomes feedback
Team collaboration is key
Working software is primary goal
Continuous improvement happens every sprint

What is a Project?

A project is a temporary effort undertaken to create a unique product, service, or result.

Key Characteristics of a Project

- Has a start and end date

- Has specific goals/objectives

- Uses limited resources

- Produces a unique outcome

- Involves planning and execution

Examples

- Developing a mobile banking app

- Building a bridge

- Organizing a conference

- Implementing ERP software

What is an IT Project?

An IT Project is a project related to information technology systems, software, hardware, networking, cloud, cybersecurity, or digital transformation.

Examples of IT Projects

- Website development

- Mobile app creation

- Cloud migration

- AI chatbot implementation

- Database migration

- Cybersecurity setup

Characteristics of IT Projects

- Technology-focused

- Frequently changing requirements

- High complexity

- Requires technical teams

- High risk of scope change

What is NOT a Project?

Activities that are routine, repetitive, and ongoing are NOT projects.

Examples

- Daily customer support

- Routine software maintenance

- Payroll processing

- Daily attendance tracking

Difference Between Project and Operations

| Project | Operations |
| --- | --- |
| Temporary | Continuous |
| Unique output | Repetitive work |
| Specific objective | Ongoing business |
| Has end date | No defined end |

What is Project Management?

Project Management is the application of knowledge, skills, tools, and techniques to project activities to achieve project objectives successfully.

Main Goals

- Complete work on time

- Stay within budget

- Deliver quality

- Meet stakeholder expectations

Advantages and Need of Project Management

Advantages

1. Better Planning

Helps define tasks, timelines, and resources.

2. Risk Management

Identifies and minimizes risks early.

3. Improved Communication

Ensures coordination among stakeholders.

4. Cost Control

Avoids unnecessary expenses.

5. Quality Improvement

Ensures standards and requirements are met.

6. Efficient Resource Utilization

Optimizes use of people and materials.

7. Customer Satisfaction

Delivers expected outcomes successfully.

Why Project Management is Needed

Project management is needed because projects are complex and involve:

- Multiple teams

- Deadlines

- Budget constraints

- Risks

- Changing requirements

Without project management:

- Projects may fail

- Costs may increase

- Deadlines may be missed

- Quality may suffer

Project Manager

A Project Manager (PM) is the person responsible for planning, executing, monitoring, and closing the project successfully.

Responsibilities

- Managing team

- Managing budget

- Managing schedule

- Risk handling

- Stakeholder communication

Roles of Project Manager

1. Planner

Creates project plans and schedules.

2. Leader

Guides and motivates the team.

3. Communicator

Communicates with stakeholders and team members.

4. Risk Manager

Identifies and mitigates risks.

5. Decision Maker

Makes project-related decisions.

6. Problem Solver

Handles conflicts and issues.

7. Quality Controller

Ensures quality standards are met.

Skills of Project Manager

Technical Skills

- Scheduling

- Budgeting

- Risk analysis

- Project tools knowledge

Leadership Skills

- Motivation

- Team management

- Delegation

Communication Skills

- Presentation

- Reporting

- Negotiation

Problem-Solving Skills

- Critical thinking

- Conflict resolution

Time Management Skills

- Prioritization

- Deadline management

Organization Structures

In Project Management, organizational structure (organization type) refers to how a company arranges its people, authority, communication, and responsibilities to manage daily operations and projects.

Types of Organization Structures

There are 3 major organizational structures:

- Functional Organization

- Matrix Organization

- Projectized Organization

Functional Organization

A Functional Organization is a project management structure where employees are grouped based on their specialized skills or functions, such as Marketing, Finance, HR, or Engineering. Each department is managed by a functional manager, and employees mainly work within their own department.

This structure is common in large organizations because it improves efficiency, clear reporting, and specialization.

Key Characteristics

- Employees are grouped by expertise or function.

- Clear hierarchy and chain of command.

- Functional managers control resources and decisions.

- Limited collaboration between departments (silo-based working).

Advantages

- Clear roles and responsibilities.

- High specialization and skill development.

- Efficient resource utilization.

- Easy performance evaluation and training.

- Stable and structured work environment.

Disadvantages

- Poor communication between departments.

- Slower decision-making across teams.

- Limited innovation due to less cross-functional collaboration.

- Employees may focus only on departmental goals instead of project goals.

When to Use

Functional organizations are best for:

- Large companies with repetitive operations.

- Organizations needing strong specialization and control.

- Stable environments with clear departmental responsibilities.

Example

In a software company:

- Developers work under the Engineering department.

- Accountants work under Finance.

- Recruiters work under HR.

If a new mobile app project starts, team members still report to their functional managers instead of a dedicated project manager.

Matrix Organization

A Matrix Organization is a project management structure where employees report to both a functional manager and a project manager. It combines the advantages of functional specialization and project-focused teamwork.

Employees work across departments to complete projects while still belonging to their functional teams.

Key Characteristics

- Dual reporting structure (functional manager + project manager).

- Cross-functional collaboration.

- Shared resources across multiple projects.

- Better communication between departments.

Types of Matrix Organization

1. Weak Matrix

The functional manager has more authority than the project manager.

Features

- Project manager acts mainly as a coordinator or expeditor.

- Functional departments control budget, resources, and decisions.

- Employees remain strongly tied to their departments.

Advantages

- Maintains strong technical expertise.

- Clear departmental control.

Disadvantages

- Project manager has limited power.

- Slow project decisions.

- Project priorities may be ignored.

Example

In a bank, the IT department controls developers while a project coordinator manages a mobile banking project with little authority.

2. Balanced Matrix

Authority is shared equally between functional managers and project managers.

Features

- Both managers participate in decisions.

- Resources and responsibilities are shared.

- Collaboration is emphasized.

Advantages

- Better teamwork and communication.

- Balanced focus on project and functional goals.

- Efficient resource sharing.

Disadvantages

- Conflicts may arise due to dual reporting.

- Employees may feel confused about priorities.

Example

In a software company, developers report to the Engineering Manager for technical work and to the Project Manager for project deadlines and deliverables.

3. Strong Matrix

The project manager has more authority than the functional manager.

Features

- Project manager controls budget, resources, and decisions.

- Teams are highly project-focused.

- Functional managers provide technical support only.

Advantages

- Faster decision-making.

- Strong project control and accountability.

- Better focus on project goals.

Disadvantages

- Functional departments may lose control.

- Resource conflicts may occur.

- Employees may feel disconnected from departments.

Example

In a construction company, the Project Manager fully manages engineers, designers, and contractors during the building project.

Advantages of Matrix Organization

- Improves cross-functional collaboration.

- Better resource utilization.

- Encourages innovation and flexibility.

- Strong focus on project objectives.

Disadvantages of Matrix Organization

- Dual reporting can create confusion.

- Conflicts between managers may occur.

- More meetings and communication overhead.

- Employees may experience stress from multiple priorities.

When to Use Matrix Organization

Matrix structures are suitable when:

- Organizations handle multiple projects simultaneously.

- Projects require collaboration from different departments.

- Resource sharing is important.

- Flexibility and innovation are needed.

Projectized Organization

A Projectized Organization is a project management structure where the organization is fully focused on projects. Employees are assigned directly to projects and report mainly to the Project Manager, who has full authority over resources, budget, and decisions.

Teams are organized around projects rather than departments.

Key Characteristics

- Project Manager has high authority.

- Teams work full-time on projects.

- Resources are dedicated to specific projects.

- Strong focus on project goals and delivery.

- Functional departments have little or no control.

Advantages

- Fast decision-making.

- Clear communication and accountability.

- Strong project focus and customer satisfaction.

- Better coordination among team members.

- High flexibility and quick problem solving.

Disadvantages

- Resource duplication may increase cost.

- Team members may feel insecure after project completion.

- Limited knowledge sharing between projects.

- Less focus on functional specialization.

When to Use

Projectized organizations are best for:

- Large, complex, or high-priority projects.

- Construction, software development, consulting, and event management industries.

- Organizations handling multiple independent projects.

- Situations requiring quick delivery and strong project control.

Example

In a construction company building a shopping mall:

- Engineers, architects, designers, and contractors work directly under the Project Manager.

- The Project Manager controls budget, schedule, and resources.

- Once the project is completed, the team may move to another project or be reassigned.

Comparison with Other Structures

- Functional Organization: Functional managers have more authority.

- Matrix Organization: Authority is shared between functional and project managers.

- Projectized Organization: Project Manager has almost complete authority.

Real-World Example

Companies involved in large infrastructure or software projects often use projectized structures, where teams are formed specifically for each project and dissolved after completion.

Comparison of Organization Structures

| Feature | Functional | Matrix | Projectized |
| --- | --- | --- | --- |
| PM Authority | Low | Medium | High |
| Flexibility | Low | Medium | High |
| Resource Sharing | High | High | Low |
| Project Focus | Low | Medium | High |
| Communication | Slow | Moderate | Fast |

Project Management Framework

A Project Management Framework provides structured guidelines and processes for managing projects effectively.

Components

- Processes

- Tools

- Templates

- Methodologies

- Best practices

Purpose

- Standardization

- Better control

- Improved success rate

PMBOK

A Guide to the Project Management Body of Knowledge

PMBOK stands for:

Project Management Body of Knowledge

It is a globally recognized project management standard developed by the Project Management Institute.

PMBOK Provides

- Best practices

- Processes

- Knowledge areas

- Tools and techniques

PMBOK Framework

PMBOK framework includes:

- Process groups

- Knowledge areas

- Inputs

- Tools & Techniques

- Outputs (ITTO)

PMBOK Knowledge Areas

PMBOK includes 10 knowledge areas.

1. Integration Management

Coordinates all project activities.

2. Scope Management

Defines and controls project scope.

3. Schedule Management

Manages project timeline.

4. Cost Management

Controls project budget.

5. Quality Management

Ensures quality standards.

6. Resource Management

Manages human and physical resources.

7. Communication Management

Ensures effective communication.

8. Risk Management

Identifies and handles risks.

9. Procurement Management

Handles purchasing and contracts.

10. Stakeholder Management

Manages stakeholder expectations.

Project Integration Management

Integration Management ensures all parts of the project work together properly.

Main Activities

- Creating project charter

- Developing project plan

- Managing changes

- Monitoring overall project work

Example

The project manager coordinates developers, testers, UI designers, and business teams to ensure the food delivery app is delivered on time.

Project Scope Management

Scope Management defines what is included and excluded in the project.

Main Activities

- Collecting requirements

- Defining scope

- Creating Work Breakdown Structure (WBS)

- Controlling scope changes

Example

The app will include:

- User login

- Restaurant search

- Order placement

- Online payment

But delivery drone support is excluded from the project scope.

Project Schedule Management

Schedule Management ensures the project finishes on time.

Main Activities

- Defining activities

- Sequencing tasks

- Estimating duration

- Creating project schedule

Example

- UI Design → 2 weeks

- Backend Development → 4 weeks

- Testing → 2 weeks

The total project duration becomes 8 weeks.

Project Cost Management

Cost Management plans and controls the project budget.

Main Activities

- Estimating costs

- Budget planning

- Cost monitoring

Example

- Developers → $20,000

- Testing → $5,000

- Cloud Hosting → $3,000

Total project budget = $28,000.

Project Quality Management

Quality Management ensures the project meets required standards.

Main Activities

- Quality planning

- Quality assurance

- Quality control

Example

The app should:

- Load within 2 seconds

- Handle 10,000 users simultaneously

- Have minimal bugs before release

Project Resource Management

Resource Management handles people, equipment, and materials needed for the project.

Main Activities

- Team formation

- Resource allocation

- Team development

Example

The project manager assigns:

- 3 Developers

- 2 Testers

- 1 UI/UX Designer

- 1 Business Analyst

Project Communication Management

Communication Management ensures the right information reaches the right people.

Main Activities

- Communication planning

- Status reporting

- Stakeholder communication

Example

- Daily Scrum meetings

- Weekly progress reports

- Monthly client review meetings

Project Risk Management

Risk Management identifies and handles project risks.

Main Activities

- Risk identification

- Risk analysis

- Risk response planning

- Risk monitoring

Example

Risk: Payment gateway API may fail.

Mitigation:

- Keep backup payment provider.

- Perform early integration testing.

Project Procurement Management

Procurement Management manages purchasing products or services from outside vendors.

Main Activities

- Vendor selection

- Contract management

- Procurement monitoring

Example

The company purchases:

- Cloud hosting services

- SMS notification API

- Third-party payment gateway

from external vendors.

Project Stakeholder Management

Stakeholder Management identifies and manages people affected by the project.

Main Activities

- Stakeholder identification

- Engagement planning

- Managing stakeholder expectations

Example

Stakeholders include:

- Customers

- Restaurant owners

- Delivery partners

- Investors

- Project team

The project manager regularly collects feedback from all stakeholders.

Summary Table

| Knowledge Area | Purpose | Example |
| --- | --- | --- |
| Integration | Coordinate entire project | Managing all app teams |
| Scope | Define project work | Features included in app |
| Schedule | Manage timeline | 8-week project plan |
| Cost | Control budget | $28,000 budget |
| Quality | Ensure standards | Fast and bug-free app |
| Resource | Manage team/resources | Assign developers/testers |
| Communication | Share project information | Daily meetings/reports |
| Risk | Handle uncertainties | Backup payment gateway |
| Procurement | Manage external purchases | Buying cloud services |
| Stakeholder | Manage involved people | Client and customer feedback |

Project Management Phases

The project lifecycle has 5 phases:

- Initiation

- Planning

- Execution

- Monitoring & Controlling

- Closing

Initiation Phase

The Initiation Phase is the very first step in the Project Lifecycle. This is where a project is formally defined, justified, and authorized to begin.

This phase answers “Should we do this project?” and “Why are we doing it?”

Purpose of Initiation Phase

The initiation phase ensures that:

- The project is valuable and feasible

- Business need or problem is clearly identified

- Key stakeholders agree to start the project

- A Project Charter is created and approved

Inputs of Initiation Phase

These are the information sources used to start the project:

Business Case

- Explains why the project is needed

- Includes cost vs benefit analysis

Example:

- Investment: $200,000

- Expected profit: $500,000 in 2 years

Agreement / Contract (if external project)

- Formal agreement between customer and company

Enterprise Environmental Factors (EEF)

Enterprise Environmental Factors are defined as conditions, not under the immediate control of the team, that influence, constrain, or direct the project.

Internal/external conditions:

- Market conditions

- Competitor analysis

- Legal rules

- Technology availability

Types of Enterprise Environmental Factors

EEF are broadly divided into Internal and External factors.

Internal EEF (within the organization)

These come from inside the company.

1. Organizational culture & structure

- Company hierarchy, policies, work style

Example:

- A strict hierarchical company requires multiple approvals before deployment

- A startup allows quick decision-making and agile changes

2. Organizational processes

- Standard operating procedures (SOPs), project governance

Example:

- Mandatory code review before merging

- Fixed procurement process for buying software tools

3. Resource availability

- People, tools, infrastructure

Example:

- Only 2 testers available → slows down testing phase

- Cloud servers shared across multiple projects

4. Employee skill sets

- Team expertise and experience

Example:

- If team lacks AI expertise, AI project slows down or needs training

5. Internal communication systems

- Email tools, Slack, Jira, meetings

Example:

- Poor communication tools may delay issue resolution

External EEF (outside organization)

These come from outside the company.

1. Government regulations & laws

- Legal and compliance requirements

Example:

- GDPR rules for data privacy in Europe

- Banking software must follow financial compliance laws

2. Market conditions

- Competition, customer demand, economic situation

Example:

- Competitor releases similar app → project scope changes

- Economic slowdown reduces budget

3. Technology trends

- Emerging tools and frameworks

Example:

- Shift from monolithic to microservices architecture

- Adoption of AI tools in testing and development

4. Political and environmental factors

- Stability, policies, natural conditions

Example:

- Political instability delays offshore project delivery

- Natural disaster affects office operations

5. External vendors and suppliers

- Third-party services or contractors

Example:

- Dependency on AWS or Azure cloud services

- Delay in delivery from outsourced development team

Real-Life Example

Project: Online Food Delivery App

EEF influencing the project:

| Type | Factor | Example Impact |
| --- | --- | --- |
| Internal | Resource availability | Only 1 backend developer → slower API development |
| Internal | Company process | Mandatory security audit before release |
| External | Legal compliance | Must follow data privacy laws for user location tracking |
| External | Market condition | Competitor offers free delivery → pricing strategy changes |
| External | Technology trend | Shift to cloud-native architecture |

Why EEF is Important

EEF helps in:

- Planning realistic timelines

- Estimating budget correctly

- Identifying risks early

- Choosing right technology stack

- Understanding constraints

Organizational Process Assets (OPA)

Organizational Process Assets (OPA) are the internal assets of an organization that help manage projects more effectively. Unlike Enterprise Environmental Factors (EEF), OPAs are owned, controlled, and updated by the organization.

In simple words:
OPA = “What the organization has learned, documented, and stored to help future projects”

They act like the knowledge bank + reusable tools + standard rules of a company.

Types of Organizational Process Assets

OPA is mainly divided into two major categories:

Processes, Policies, and Procedures

These are rules and structured ways of working.

1. Project Management Processes

- Standard steps followed in projects

Example:

- Requirement gathering template

- Change request approval process

- Risk management procedure

2. Organizational Policies

- Company rules that guide project work

Example:

- Security policy: All applications must pass penetration testing

- HR policy: Maximum 40 working hours per week

- Procurement policy: Any purchase above $5000 needs CFO approval

3. Standard Templates and Guidelines

- Ready-made documents used in projects

Example:

- Project charter template

- Risk register template

- Test case template

- Status report format

4. Communication Guidelines

- How information is shared in the organization

Example:

- Weekly sprint review meeting format

- Standard escalation matrix

- Jira workflow rules for issue tracking

B. Organizational Knowledge Base

This is historical knowledge stored from past projects.

1. Lessons Learned Repository

- Experience from past projects (success + failures)

Example:

- “API integration delays happened due to unclear requirements → next time involve client early”

- “Using microservices improved scalability in previous project”

2. Historical Information

- Data from previous projects

Example:

- Past project timelines

- Actual vs planned cost reports

- Productivity rates of teams

3. Project Files and Documentation

- Stored project artifacts

Example:

- Old requirement documents

- Architecture diagrams

- Test reports from previous releases

4. Issue and defect logs

- Records of past problems and resolutions

Example:

- “Login failure issue fixed by updating authentication token logic”

- Known bug database used for regression testing

Real-Life Example

Project: Online Food Delivery App

OPA used in the project:

| OPA Type | Example | Benefit |
| --- | --- | --- |
| Template | Standard user story format in Jira | Faster requirement writing |
| Process | Change request approval workflow | Controlled scope changes |
| Lessons learned | Previous app failed due to poor delivery tracking | Improved GPS integration early |
| Historical data | Past sprint velocity = 30 story points | Better sprint planning |
| Guidelines | UI design system standards | Consistent UI across app |

Why OPA is Important

OPA helps project teams:

- Save time (no need to reinvent processes)

- Improve consistency across projects

- Reduce mistakes using past lessons

- Standardize documentation

- Improve project success rate

Tools & Techniques Used

These are methods used to evaluate and approve the project:

Expert Judgment

- Experts evaluate whether project is feasible

- Example: Senior IT architect reviews app idea

Feasibility Study

Checks whether project is possible:

- Technical feasibility (Can we build it?)

- Financial feasibility (Is it affordable?)

- Operational feasibility (Will users adopt it?)

SWOT Analysis

SWOT Analysis is a strategic planning tool used to evaluate an organization’s Strengths, Weaknesses, Opportunities, and Threats. It helps businesses understand their internal capabilities and external environment to make better decisions.

In an IT company, SWOT is widely used for product strategy, market expansion, competitive analysis, and project planning.

SWOT stands for:

- S – Strengths (Internal, Positive)

- W – Weaknesses (Internal, Negative)

- O – Opportunities (External, Positive)

- T – Threats (External, Negative)

Strengths (Internal Advantages)

These are what the IT company does well.

Examples in IT Company:

- Strong technical team (AI, cloud, cybersecurity experts)

- Established brand reputation (e.g., trusted software provider)

- Advanced R&D capabilities

- Strong product portfolio (SaaS platforms, enterprise tools)

- High customer retention rate

- Scalable cloud infrastructure

Example:

A company like Google has strength in:

- Search engine dominance

- AI research leadership

- Massive data infrastructure

Weaknesses (Internal Limitations)

These are internal problems that reduce performance.

Examples in IT Company:

- High employee turnover in developers

- Legacy systems (old technology stack)

- Weak marketing strategy

- Limited global presence

- High dependency on one product or client

- Slow innovation cycle

Example:

An IT startup may struggle with:

- Lack of experienced senior developers

- Poor documentation practices

- Limited funding

Opportunities (External Growth Factors)

These are external chances to grow or improve.

Examples in IT Industry:

- Growing demand for AI and machine learning solutions

- Cloud computing expansion (AWS, Azure, GCP adoption)

- Digital transformation in healthcare, banking, education

- Remote work increasing need for collaboration tools

- Cybersecurity demand due to rising cyber attacks

- Expansion into emerging markets

Example:

A SaaS company can grow by:

- Launching AI-based automation tools

- Expanding services in Asia or Africa

Threats (External Risks)

These are external factors that can harm the business.

Examples in IT Company:

- Strong competition (Microsoft, Amazon, startups)

- Rapid technology changes (AI replacing traditional tools)

- Cybersecurity risks and data breaches

- Economic slowdown affecting IT budgets

- Government regulations (data privacy laws like GDPR)

- Talent shortage in tech industry

Example:

A software company may lose market share due to:

- New AI-powered competitors offering cheaper solutions

Cost-Benefit Analysis

- Compare cost of project vs expected benefits

Brainstorming / Meetings

- Stakeholders discuss project ideas

Data Analysis

- Market research

- User surveys

Outputs of Initiation Phase

This phase produces key deliverables:

Project Charter

A Project Charter is a formal document that:

- Officially authorizes the project

- Defines high-level project objectives

- Identifies stakeholders

- Gives authority to the Project Manager

- Serves as the foundation of the project

It is a document issued by the project initiator or sponsor that formally authorizes the existence of a project.

Simple Meaning

Think of it like:

“A legal permission letter to start a project.”

Without it, the project has no official approval.

Why is Project Charter Needed?

✔ Official Approval

It formally approves that the project exists.

✔ Gives Authority to Project Manager

PM gets power to:

- Use resources

- Assign tasks

- Communicate with stakeholders

✔ Aligns Stakeholders

Everyone understands:

- What is being built

- Why it is being built

✔ Prevents Confusion

Avoids unclear goals and scope creep at early stage.

✔ Foundation for Planning

All future documents depend on it:

- Scope statement

- Schedule

- Budget plan

Key Components of Project Charter

A standard Project Charter contains:

1. Project Title

Name of the project
Example: “Online Food Delivery App Development”

2. Project Purpose / Justification

Why the project is needed
Example:

- Improve online food ordering experience

- Compete with existing apps

3. Objectives (High-Level Goals)

What the project wants to achieve

Example:

- Develop mobile app in 6 months

- Support real-time order tracking

- Achieve 50,000 users in first 3 months

4. High-Level Scope

What is included and excluded (very general)

Example:
Included:

- Android & iOS app

- Payment integration

Excluded:

- Restaurant hardware setup

5. Key Stakeholders

People involved or affected:

- Project Sponsor

- Project Manager

- Developers

- Customers

- Vendors

6. Project Manager Assigned

Name and authority of PM

Example:

- PM: John Smith

- Authority: full control over development team

7. Milestones (High-Level Timeline)

Example:

- Requirement gathering: 2 weeks

- Development: 3 months

- Testing: 1 month

- Launch: Month 6

8. Budget Overview

Example:

- Total budget: $200,000

- Infrastructure: $50,000

- Development: $100,000

- Marketing: $50,000

9. Risks (High-Level)

Example:

- Delay in development

- High competition

- Security vulnerabilities

10. Assumptions & Constraints

Assumptions:

- Team is available full-time

- APIs will be accessible

Constraints:

- Fixed budget

- Must launch in 6 months

11. Approval Section

Includes:

- Sponsor name

- Signature

- Date

Example Project Charter (IT Company)

Project: “FoodExpress Mobile App”

1. Purpose

Develop a mobile app for online food ordering to increase customer reach and improve delivery efficiency.

2. Objectives

- Build Android & iOS app within 5 months

- Integrate payment gateway

- Achieve 10,000 users in first month after launch

3. Scope

✔ In Scope:

- User registration

- Restaurant listing

- Order placement

- Payment integration

❌ Out of Scope:

- Restaurant POS system integration

4. Stakeholders

- Sponsor: CEO of FoodExpress

- Project Manager: Sarah Khan

- Development Team: 8 engineers

- Customers: End users

5. Timeline

- Planning: 2 weeks

- Design: 3 weeks

- Development: 3 months

- Testing: 1 month

6. Budget

- Total: $150,000

7. Risks

- Third-party API failure

- Delays in UI/UX design

- High competition from existing apps

8. Project Manager Authority

- Full control over development team

- Resource allocation approval

9. Approval

Approved by: CEO
Date: 28 May 2026

Simple Flow of Initiation Phase

Business Need → Feasibility Study → Business Case → Approval → Project Charter → Stakeholders Identified

Stakeholder Register

A Stakeholder Register is a document that:

- Lists all stakeholders involved in the project

- Records their roles, expectations, influence, and interests

- Helps the project team manage communication and engagement

Why is Stakeholder Register Important?

✔ Identifies all stakeholders

Ensures no important person/group is missed.

✔ Helps communication planning

You know:

- Who needs updates

- How often they need updates

✔ Manages expectations

Prevents conflicts later.

✔ Improves risk management

Stakeholders can support or block project success.

✔ Supports decision making

Helps prioritize stakeholder needs.

When is it created?

- Created during Initiation phase

- Updated throughout the project lifecycle

Components of Stakeholder Register

A typical stakeholder register includes:

1. Stakeholder Name

Individual or group name

Example:

- John Smith

- IT Department

- External Vendor

2. Role / Position

Their function in the project

Example:

- Project Sponsor

- Developer

- Customer

- Supplier

3. Contact Information

Email, phone, or department

4. Stakeholder Type

Internal or External:

- Internal → employees, managers

- External → customers, vendors, regulators

5. Interest Level

How much they care about the project:

- High

- Medium

- Low

6. Influence / Power

Ability to affect the project:

- High influence (CEO)

- Medium (Project Manager)

- Low (end user)

7. Expectations / Requirements

What they expect from the project

Example:

- Fast delivery

- Low cost

- High quality UI

8. Engagement Strategy

How to manage them:

- Keep satisfied

- Keep informed

- Actively involve

- Monitor only

Project: Online Food Delivery App

| Stakeholder | Role | Type | Interest | Influence | Expectations | Engagement Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| CEO | Project Sponsor | Internal | High | High | Business growth, ROI | Keep satisfied |
| Project Manager | PM | Internal | High | High | Successful delivery | Actively involve |
| Developers | Dev Team | Internal | High | Medium | Clear requirements | Keep informed |
| Customers | End Users | External | High | Low | Easy app, fast delivery | Collect feedback |
| Restaurant Partners | Vendors | External | Medium | Medium | More orders | Keep informed |
| Payment Gateway Provider | Vendor | External | Medium | Medium | Secure integration | Manage closely |

Planning Phase

The Project Planning Phase is the second phase of the project life cycle, where the project team defines how the project will be executed, monitored, and controlled. It converts the high-level idea from the Initiation phase into a clear, actionable roadmap.

The Project Planning Phase is the process of:

- Defining project scope in detail

- Creating schedules, budgets, and resource plans

- Identifying risks and mitigation strategies

- Establishing communication and quality plans

Simple meaning:

“Planning phase decides HOW the project will be done.”

Why Planning Phase is Important?

✔ Clear Direction

Avoids confusion during execution.

✔ Reduces Risks

Identifies risks early.

✔  Better Resource Management

Ensures right people, time, and budget.

✔ 4. Improves Success Rate

Well-planned projects are more likely to succeed.

✔ Baseline for Execution

Acts as reference for monitoring progress.

Project Planning Phase — Key Inputs, Tools, Outputs

Inputs (What you need before planning)

Project Charter

- High-level project approval document

- Defines goals, scope, and sponsor

Stakeholder Register

- Identifies stakeholders and their needs

EEF (Enterprise Environmental Factors)

External/internal conditions like:

- Company culture

- Market conditions

- Legal rules

- Technology environment

OPA (Organizational Process Assets)

Internal company resources:

- Templates

- Policies

- Past project data

- Lessons learned

Tools & Techniques (How planning is done)

Expert Judgment

- Experienced managers guide planning

Brainstorming

- Generate ideas and solutions

Meetings & Workshops

- Team discussions for scope, risks, etc.

Work Breakdown Structure (WBS)

- Breaking project into smaller tasks

A Work Breakdown Structure (WBS) is a hierarchical decomposition of the total project work into smaller, manageable components. It helps the project team organize and define all the work needed to complete the project successfully.

A Work Breakdown Structure (WBS) is a deliverable-oriented hierarchical breakdown of the work to be executed by the project team.

“Breaking a large project into smaller tasks until the work becomes easy to manage.”

Why WBS is Important?

✔ Better Project Organization

Large projects become manageable.

✔ Easier Task Assignment

Each task can be assigned to specific team members.

✔ Better Time & Cost Estimation

Smaller tasks are easier to estimate.

✔ Improves Tracking & Monitoring

Progress can be tracked at each level.

✔ Reduces Missing Work

Ensures all project work is identified.

Key Characteristics of WBS

| Characteristic | Description |
| --- | --- |
| Hierarchical | Organized in levels |
| Deliverable-oriented | Focuses on outputs |
| Decomposition | Breaks work into smaller pieces |
| 100% Rule | Includes all project work |
| Manageable Units | Small enough to estimate and control |

WBS Hierarchy Levels

A WBS is usually divided into levels:

| Level | Description |
| --- | --- |
| Level 1 | Project |
| Level 2 | Major Deliverables |
| Level 3 | Sub-deliverables |
| Level 4 | Work Packages |

What is a Work Package?

The lowest level of WBS is called a Work Package.

It is:

- Small enough to estimate

- Assignable to one person/team

- Trackable and measurable

Example of WBS (IT Project)

roject: Online Food Delivery System

1. Online Food Delivery System
│
├── 1.1 Requirement Analysis
│   ├── 1.1.1 Gather Requirements
│   ├── 1.1.2 Stakeholder Meetings
│   └── 1.1.3 Requirement Documentation
│
├── 1.2 System Design
│   ├── 1.2.1 UI/UX Design
│   ├── 1.2.2 Database Design
│   └── 1.2.3 Architecture Design
│
├── 1.3 Development
│   ├── 1.3.1 Frontend Development
│   ├── 1.3.2 Backend Development
│   ├── 1.3.3 API Integration
│   └── 1.3.4 Payment Gateway Integration
│
├── 1.4 Testing
│   ├── 1.4.1 Unit Testing
│   ├── 1.4.2 Integration Testing
│   ├── 1.4.3 System Testing
│   └── 1.4.4 User Acceptance Testing
│
└── 1.5 Deployment
    ├── 1.5.1 Server Setup
    ├── 1.5.2 Production Deployment
    └── 1.5.3 User Training

Visual WBS Diagram

Online Food Delivery System
                               │
 ┌───────────────┬───────────────┬───────────────┬───────────────┐
 Requirement     Design        Development       Testing      Deployment
 Analysis

Advantages of WBS

✔ Better planning
✔ Accurate estimation
✔ Easier tracking
✔ Improved communication
✔ Better risk identification

Simple Summary

WBS is:

✔ A hierarchical breakdown of project work
✔ Used to organize and manage project tasks
✔ Helps in estimation, scheduling, and monitoring
✔ Ends with manageable work packages

Scheduling Tools

- Gantt charts

- Critical Path Method (CPM)

Estimation Techniques

- Analogous estimation

- Parametric estimation

- Bottom-up estimation

Risk Analysis Tools

- SWOT analysis

- Risk probability & impact matrix

A Risk Probability and Impact Matrix is a project risk management tool used to:

- Evaluate project risks

- Prioritize risks

- Decide which risks need immediate attention

It helps the project team understand:

“Which risks are most dangerous to the project?”

What is Risk Probability & Impact Matrix?

It is a grid/table that measures risks based on:

- Probability → How likely the risk is to happen

- Impact → How severe the effect will be if it happens

The combination determines the risk severity level.

Why is it Needed?

✔ Prioritize Risks

Not all risks are equally important.

✔ Better Decision Making

Focus resources on high-priority risks.

✔ Improves Risk Response Planning

Helps decide mitigation actions.

✔ Reduces Project Failure Chances

Early identification prevents major problems.

Key Concepts

Probability

Probability means:

“Chance that the risk will occur”

Usually expressed as:

- Percentage

- Scale (1–5)

Example Probability Scale

| Score | Probability | Meaning |
| --- | --- | --- |
| 1 | Very Low | Rare |
| 2 | Low | Unlikely |
| 3 | Medium | Possible |
| 4 | High | Likely |
| 5 | Very High | Almost certain |

Impact

Impact means:

“How much damage the risk can cause”

Can affect:

- Cost

- Schedule

- Quality

- Scope

- Security

Example Impact Scale

| Score | Impact | Meaning |
| --- | --- | --- |
| 1 | Very Low | Minimal effect |
| 2 | Low | Small delay/cost |
| 3 | Medium | Noticeable issue |
| 4 | High | Serious problem |
| 5 | Very High | Project failure possible |

Risk Score Formula

Many organizations calculate:

Risk Score=Probability×Impact

Detailed IT Project Example

Project: Online Banking Application

Step 1: Identify Risks

| Risk ID | Risk Description |
| --- | --- |
| R1 | Cybersecurity attack |
| R2 | Developer resignation |
| R3 | Delay in API integration |
| R4 | Server outage |
| R5 | Requirement changes |

Step 2: Assign Probability & Impact

| Risk | Probability | Impact |
| --- | --- | --- |
| Cybersecurity attack | 4 | 5 |
| Developer resignation | 3 | 3 |
| API delay | 4 | 4 |
| Server outage | 2 | 5 |
| Requirement changes | 5 | 3 |

Step 3: Calculate Risk Score

| Risk | Probability | Impact | Score |
| --- | --- | --- | --- |
| Cybersecurity attack | 4 | 5 | 20 |
| Developer resignation | 3 | 3 | 9 |
| API delay | 4 | 4 | 16 |
| Server outage | 2 | 5 | 10 |
| Requirement changes | 5 | 3 | 15 |

Step 4: Prioritize Risks

| Risk | Level | Action |
| --- | --- | --- |
| Cybersecurity attack | Critical | Immediate mitigation |
| API delay | Critical | Escalate & monitor daily |
| Requirement changes | High | Strong change control |
| Server outage | Medium | Backup server setup |
| Developer resignation | Medium | Cross-training |

Software Tools

- MS Project

- Jira

- Trello

Outputs (What you get after planning)

Project Management Plan (Main Output)

This is the master document containing:

- Scope management plan

- Schedule management plan

- Cost management plan

- Quality management plan

- Risk management plan

- Communication plan

- Resource plan

Scope Baseline

Includes:

- Project scope statement

- WBS

- WBS dictionary

Schedule Baseline

- Final approved timeline

Cost Baseline

- Approved budget plan

Risk Register

- List of risks and mitigation plans

Communication Plan

- Who gets what information, when, and how

Resource Management Plan

- Team roles and responsibilities

Example: IT Project Planning Phase

Project: Online Food Delivery App

Inputs

- Project Charter approved by CEO

- Stakeholder Register (customers, restaurants, dev team)

- Company policies (Agile methodology)

- Past mobile app project data

Planning Activities

Scope Planning

- Features:

  - User login

  - Order food

  - Payment integration

WBS Creation

- Level 1: Food Delivery App

  - Level 2: Frontend

  - Level 2: Backend

  - Level 2: Payment system

  - Level 2: Testing

Schedule Planning

- Design: 3 weeks

- Development: 3 months

- Testing: 1 month

Cost Estimation

- Total budget: $150,000

  - Developers: $80,000

  - Design: $20,000

  - Testing: $30,000

  - Marketing: $20,000

Risk Planning

| Risk | Mitigation |
| --- | --- |
| Payment gateway failure | Use backup provider |
| Delay in development | Add extra developers |
| Security breach | Use encryption & testing |

Communication Plan

- Weekly meetings with team

- Monthly report to CEO

- Daily standup (Agile)

Outputs

- Project Management Plan created

- WBS finalized

- Schedule baseline approved

- Cost baseline fixed

- Risk register created

Simple Summary

Project Planning Phase is:

✔ The roadmap of the project
✔ Defines what, how, when, and by whom work will be done
✔ Produces detailed documents like WBS, schedule, budget, risk plan

Execution Phase

The Execution Phase is the phase where the actual project work is performed to produce the project deliverables.

It is the stage where:

- Plans are implemented

- Teams perform tasks

- Products/services are developed

- Resources are utilized

“Execution Phase = Doing the actual project work.”

The Execution Phase involves processes performed to complete the work defined in the project management plan to satisfy project requirements.

Main Objective of Execution Phase

The primary goal is:

✔ Deliver project outputs
✔ Build the actual product/service
✔ Manage team and resources
✔ Ensure quality work
✔ Communicate with stakeholders

Major Activities in Execution Phase

Team Management

Project Manager:

- Assigns tasks

- Motivates team

- Resolves conflicts

- Tracks performance

Example

Assign:

- Frontend tasks to UI developers

- API tasks to backend team

Task Execution

The team starts actual work:

- Coding

- Designing

- Testing

- Infrastructure setup

Resource Management

Managing:

- Human resources

- Budget

- Equipment

- Software tools

Communication Management

Continuous communication with:

- Stakeholders

- Clients

- Team members

Examples:

- Daily standups

- Weekly reports

- Sprint reviews

Quality Assurance

Ensuring work follows quality standards.

Examples:

- Code review

- QA processes

- Compliance checks

Procurement Management

Managing vendors and external services.

Example:

- Purchasing cloud servers

- Hiring third-party security testers

Risk Response Implementation

Executing mitigation plans for identified risks.

Example:

- Backup servers prepared for downtime risk

Inputs of Execution Phase

Project Management Plan

Main guide for execution.

Includes:

- Scope

- Schedule

- Budget

- Quality plans

Project Documents

- Risk register

- Stakeholder register

- Requirements documentation

Approved Change Requests

Authorized modifications from planning/monitoring phases.

Enterprise Environmental Factors (EEF)

- Organizational culture

- Infrastructure

- Regulations

Organizational Process Assets (OPA)

- Policies

- Templates

- Best practices

Tools & Techniques Used

Expert Judgment

Senior experts guide execution.

Project Management Information Systems (PMIS)

Examples:

- Jira

- Trello

- Asana

- MS Project

Meetings

- Daily standups

- Status meetings

- Technical discussions

Interpersonal Skills

- Leadership

- Conflict management

- Negotiation

Quality Management Tools

Examples:

- Code review

- Test automation

- CI/CD pipelines

Outputs of Execution Phase

Deliverables

Actual outputs produced.

Examples:

- Software modules

- APIs

- Mobile app

Work Performance Data

Raw execution data:

- Tasks completed

- Defects found

- Time spent

Issue Log

Records project issues/problems.

Change Requests

Requested modifications discovered during execution.

Project Document Updates

Updated:

- Risk register

- Schedule

- Stakeholder communication

Detailed IT Project Example

Project: Online Food Delivery App

Inputs

- Approved project plan

- WBS

- Schedule baseline

- Budget baseline

- Team assignments

Execution Activities

Step 1: Team Assignment

| Team | Responsibility |
| --- | --- |
| Frontend Team | Mobile UI |
| Backend Team | APIs & database |
| QA Team | Testing |
| DevOps Team | Deployment |

Step 2: Development Starts

Frontend Team

Builds:

- Login screen

- Food menu

- Cart system

Backend Team

Builds:

- Order APIs

- Authentication system

- Payment integration

Step 3: Communication

- Daily Scrum meetings

- Weekly stakeholder report

- Sprint demo every 2 weeks

Step 4: Quality Assurance

QA team performs:

- Unit testing

- Integration testing

- Security testing

Step 5: Risk Handling

Risk:

Payment gateway API delay

Action:

Use mock API temporarily

Outputs

| Output | Example |
| --- | --- |
| Deliverables | Working mobile app |
| Work Performance Data | 80% tasks completed |
| Change Request | Add dark mode |
| Issue Log | Payment timeout issue |

Real-World Example

Example: Building an E-commerce Website

During execution:

- Designers create UI

- Developers code features

- QA tests functions

- DevOps deploys servers

- PM manages schedule & communication

Common Problems During Execution

❌ Scope creep
❌ Team conflicts
❌ Delays
❌ Budget overrun
❌ Poor communication
❌ Quality defects

Scope Creep is the uncontrolled or gradual expansion of a project’s scope without proper approval, planning, or adjustment to time, cost, and resources.

It happens when new requirements or changes are added after the project has started.

Best Practices

✔ Regular meetings
✔ Clear communication
✔ Continuous monitoring
✔ Strong leadership
✔ Early issue resolution
✔ Agile feedback loops

Execution Phase in Agile

In Agile execution:

- Work happens in sprints

- Daily standups occur

- Continuous delivery is common

- Customer feedback is frequent

Simple Summary

Execution Phase is:

✔ The phase where actual project work happens
✔ Teams build the deliverables
✔ PM manages people, quality, communication, and risks
✔ Produces the final product incrementally

Monitoring and Controlling Phase

The Monitoring and Controlling Phase is the phase where project performance is continuously tracked, reviewed, and regulated to ensure the project stays aligned with the plan.

It runs throughout the project, especially during execution.

Monitoring and Controlling consists of processes required to track, review, and regulate the progress and performance of the project.

The main goals are:

✔ Measure project performance
✔ Compare actual vs planned progress
✔ Detect issues early
✔ Control scope, cost, schedule, and quality
✔ Take corrective actions

What is Monitored?

Project managers monitor:

| Area | Example |
| --- | --- |
| Scope | Extra features added? |
| Schedule | Are tasks delayed? |
| Cost | Is budget exceeded? |
| Quality | Are defects increasing? |
| Risks | Did risks occur? |
| Resources | Is team overloaded? |
| Communication | Are stakeholders informed? |

Key Activities in Monitoring & Controlling

Performance Measurement

Compare:

- Planned work vs Actual work

Examples:

- Planned completion = 80%

- Actual completion = 60%

👉 Indicates delay.

Schedule Control

Checks if project is on time.

Tools:

- Gantt chart

- Burndown chart

- Critical Path Method

Cost Control

Monitors spending.

Example:

- Budget planned = $50,000

- Actual spent = $70,000

👉 Budget overrun detected.

Scope Control

Prevents scope creep.

Example:
Client requests extra feature:

- PM evaluates impact

- Formal approval required

Quality Control

Checks deliverables for defects.

Activities:

- Testing

- Inspections

- Code review

Risk Monitoring

Tracks:

- Existing risks

- New risks

- Effectiveness of mitigation

Change Control

Manages project changes formally.

Steps:

- Request change

- Analyze impact

- Approve/reject

- Update plans

Inputs of Monitoring & Controlling Phase

Project Management Plan

Baseline reference.

Includes:

- Scope baseline

- Schedule baseline

- Cost baseline

Work Performance Data

Collected from execution.

Examples:

- Tasks completed

- Defects found

- Hours worked

Project Documents

- Risk register

- Issue log

- Schedule

- Quality reports

Tools & Techniques Used

Earned Value Management (EVM)

Measures project performance.

Common metrics:

- PV (Planned Value)

- EV (Earned Value)

- AC (Actual Cost)

Example Formula

Schedule Variance:

SV=EV-PV

Cost Variance:

CV=EV-AC

Variance Analysis

Finds difference between planned and actual results.

Meetings

Examples:

- Status meetings

- Sprint reviews

- Risk review meetings

Project Management Software

Examples:

- Jira

- Trello

- MS Project

- Azure DevOps

Data Analysis Tools

- Trend analysis

- Root cause analysis

- Forecasting

Outputs of Monitoring & Controlling

Work Performance Reports

Reports showing:

- Progress

- KPIs

- Issues

Change Requests

Suggested modifications to:

- Scope

- Budget

- Schedule

Updated Project Documents

Updated:

- Risk register

- Schedule

- Cost estimates

Corrective Actions

Actions to bring project back on track.

Example:

- Add more developers to recover delay

Preventive Actions

Actions to avoid future problems.

Example:

- Introduce automated testing early

Project: Online Food Delivery App

During Execution

Development begins:

- Login feature completed

- Payment module delayed

Monitoring Activities

1. Schedule Monitoring

Planned:

- Payment integration complete by Week 4

Actual:

- Only 50% complete

👉 Delay identified.

2. Cost Monitoring

Budget:

- $100,000

Actual spending:

- $120,000

👉 Budget overrun detected.

3. Quality Monitoring

QA team finds:

- Payment failures

- Security vulnerabilities

👉 Additional testing required.

4. Scope Monitoring

Client requests:

- Voice ordering feature

PM:

- Creates change request

- Estimates extra cost/time

5. Risk Monitoring

Risk:

- Third-party payment API instability

Mitigation:

- Backup payment gateway prepared

Outputs

| Output | Example |
| --- | --- |
| Performance Report | 70% work completed |
| Change Request | Add voice ordering |
| Corrective Action | Increase testing resources |
| Updated Risk Register | Added API outage risk |

Monitoring vs Controlling

| Monitoring | Controlling |
| --- | --- |
| Observing performance | Taking corrective action |
| Detecting problems | Fixing problems |
| Example: detecting delay | Example: adding developers |

Common Problems Found During Monitoring

❌ Scope creep
❌ Budget overrun
❌ Delays
❌ Poor quality
❌ Resource overload
❌ Stakeholder dissatisfaction

Best Practices

✔ Continuous tracking
✔ Frequent communication
✔ Early risk identification
✔ Use dashboards & reports
✔ Strong change management

Agile Monitoring & Controlling

In Agile:

- Burndown charts track progress

- Sprint reviews gather feedback

- Retrospectives improve process

- Continuous testing ensures quality

Simple Summary

Monitoring & Controlling Phase:

✔ Tracks project performance
✔ Compares planned vs actual work
✔ Detects issues and risks
✔ Implements corrective actions
✔ Ensures project stays on track

Closing Phase

Purpose

Formally complete the project.

Activities

- Final delivery

- Documentation

- Lessons learned

- Contract closure

Inputs

- Accepted deliverables

- Project documents

Tools & Techniques

- Meetings

- Audits

- Expert judgment

Outputs

- Final product/service

- Final report

- Lessons learned document

- Project closure report